## Mag Landing Vol Alt Log 7-29
[6 empty] | VE Item List | VE Item List |  |  | Accepted
Item | Div |  | Schedule of Voluntary Alternates to 60% Working Budget 8-31-26 |  | ADD/ (DEDUCT) CF Evans Budget Change Values | ADD Values | (DEDUCT) Values |  | Owner Worksheet | Accepted Target Items by OCA Team
|  | Apply to | Broad Creek Apartments - Hilton Head SC WORKSHEET | [5 empty] | YES
1 | 01 |  | Site Security Cameras: Add Allowance to provide Site Security Cameras if Builders Risk Policy requires or OCA requests - suggest use $80K |  |  | 80000
2 |  |  | 02Special Sitework
3 | 02 |  | Dock reconstruction : Reuse the first 34 existing piles in the first 272 feet - appear OK |  |  |  | -48000
4 | 02 |  | Dock Demo Only Demolish Existing Dock - No Build back New Dock ($40K Demo) |  |  |  | -338981
5
6
7
8 |  |  | Sitework :
9 | 02 | 06 | Delete AGG Piers for Buildings F and G - use 2000 PSF |  |  |  | TBD
10 | 02 |  | Landscape / Hardscapes:
11 | 02 | 06 | This scope requires an itemized review to decide on VE Items |  |  |  | TBD
12 | 03 |  | Gypcrete
13 | 03 |  | Upgrade Sound Mat from 1/4" tp 3/4" |  |  | Upon Request
14 | 04 |  | Masonry
15 | 04 |  | BRICK: Base Bid assumes Modular Brick carried at $400/M - Adjust from Final Brick selection |  |  |  | TBD
16 | 04 |  | Upgrade mortar from standard to colored mortar at $22/ Bag allowance |  |  | 84916
17 | 05 |  | Metals and Rails
18 | 05 |  | Balcony Screens: Delete Balcony Screens on 184 Units (31,888 SF) |  |  |  | -414505
19 | 06 |  | Cabinetry
20 |  |  | Delete Undercabinet Lighting and Electrical |  |  |  | -146925
21 |  |  | Delete Full Extension Drawer Glides and Soft Close Doors |  |  |  | -45295
22 |  |  | Use Delta Flat Panel Doors in lieu of Skinny Shaker door style |  |  |  | -42000
23 |  |  | Use Granite Level 1 countertops In Lieu of Quartz Level 1 |  |  |  | -101920
24 | 07 |  | Insulation
25 |  |  | UNITS: Add Interior sound insulation in Units |  |  | 61950
26 | 07 |  | Attic Insulation on flat roofs ILO Dry System Sprinklers |  |  |  | TBD
27 | 07 |  | Roofs
28 | 07 |  | Delete Standing Seam Metal Roofs, Replace with Shingle Roofs |  |  |  | -325000
29 | 07 |  | Deduct Fully Adhered TPO Roof systems, replace with Mechanically attached TPO roofs |  |  |  | -45000
30 | 07 |  | Upgrade to 5" Round Downspouts from 4" provided |  |  | 160000
31 | 07 |  | Siding
32 | 07 |  | Balcony ceilings are provided as Hardie material - replace with exterior drywall material |  |  |  | -150000
33 | 07 |  | Eliminate Brackets at top level apartments |  |  |  | -96960
34 | 07 |  | Eliminate Brackets at at First Level apartments |  |  |  | -28880
35 | 07 |  | Eliminate Brackets at Clubhouse and Fitness buildings |  |  |  | -35720
36 | 07 |  | Eliminate Decorative Rafter Tails |  |  |  | -55440
37 | 08 |  | Doors and Windows
38 | 08 |  | Delete Elevator Smoke Curtains if Arch can design them out - Added by CFE - Not Shown |  |  |  | -126000
39 | 08 |  | ADD Blinds between the Glass on Balcony Doors - No Grids |  |  | 93916
40 | 08 |  | Delete Transoms over doors |  |  |  | -51000
41 | 08 |  | Delete Transoms over windows |  |  |  | -47500
42 | 09 |  | Finishes: :
43 | 09 |  | Use RC Deluxe Ceiling Channel in lieu of RC-1 |  |  | 101600
44 | 09 |  | Use Flat paint on unit walls in lieu of Matte/Eggshell |  |  |  | -88900
45 | 09 |  | Flooring Units: LVT Use Kantanga 2MM 12Mil ILO Kings Tide |  |  | 31000
46 | 09 |  | Flooring Units: : LVT Use Kings Tide 2MM 12Mil with Acoustical Backing |  |  | 417926
47 | 09 |  | Flooring Penthouse: Use Kings Tide 4MM 12mil acoustical Plank ILO Kings Tide 2MM 12 mil |  |  | 9100
48 | 09 |  | Flooring Penthouse Large Bath Floors - USE UT-5 Herringbone Tile Mosaic Add |  |  | 12300
49 | 09 |  | Flooring Penthouse Large Bath Floors - USE Kings Tide 4MM 12mil acoustic Plank |  |  | 1000
50 | 09 |  | Tub Surround : Use Kings Tide Moultrie 3x10 ILO GST 3x12 Deduct |  |  |  | -75000
51 | 09 |  | Penthouse Tub Surrounds: Change UT-4 to similar from Kings Tide |  |  |  | -7680
52 | 09 |  | Kitchen Backsplash: To Change UT -3 to similar Tile from Kings Tide Deduct |  |  |  | -12000
53 | 09 |  | Corridor Carpet : Use a Carpet at $35/ SY Installed ILO Bently Corridor Carpet Deduct |  |  |  | -43380
54 | 10 |  | Specialties | SPECIALITIES : |  |  |  | SPECIALITIES : |  |  | SPECIALITIES :
55 | 10 |  | Lighted Mirrors: Replace Lighted vanity mirrors with regular framed mirrors |  |  |  | -56500
56 | 11 |  | Appliances
57 | 11 |  | Deduct 242 ea. Countertop Microwaves shown installed in Pantry Cabinets + Over Range Hoods and ADD Over Range Microwaves instead (Note: this offer due to concern of heat build up from counter Microwaves in cabinetry) - See Electrolux Caution, Fire Risk) |  |  |  | -43864
58 | 11 |  | Deduct 242 ea. Countertop Microwaves shown installed in Pantry Cabinets + Over Range Hoods and ADD 2.2 CF 1000 watt drawer style Microwaves instead - cabinetry to be modified |  |  | 156220
59 | 10 | 06 | Window Treatment - Units
60 | 12 | 06 | Roller Shades: Replace 2" Faux wood blinds on windows and balcony doors with 1% Openness Roller Shades |  |  | 319935
61 |  |  | POOL:
62 | 13 | 09/15 | The Base Bid Pool is 4,155 SF : Downsize The Pool at OCA discretion and Instructions |  |  |  | TBD
63 | 13 |  | The Spa is 147 SF with HC Lift Chair - DELETE the Spa |  |  |  | -125000
64 | 14 |  | ELEVATORS
65 | 14 |  | Replace the Schlindler 2100 Lb. Clubhouse Elev with LULA Elevator by Savaria Orion - ADD |  |  | 70477
66 | 14 |  | Deduct for 7 ft hall doors (ILO 8ft) and 7ft 9" Cab heights (ILO 9ft) Schlindler Elevator 4 Elevators |  |  |  | -250000
67 | 15 |  | FIRE SPRINKLER:
68 | 15 |  | Replace Dry Sprinklers under flat roof wells with Dense Pack insulation in attic truss cavity |  |  |  | TBD
69 |  |  | Electric
70 | 16 |  | Electric Breakers: Delete the GFI requirement for stove and dryers - allowed by Code |  |  |  | -38100
71 | 16 |  | If required by Local AHJ to upgrade to 520 Hz smoke detectors in units - |  |  | 165400
72 |  | 04 | TOTAL Worksheet
1